Celebrate Fremont

Fundraising Committee Minutes

July 25, 2005

Attendees: (X Denotes Present)

| X | Jack Rogers | X | Les Mensinger |
| --- | --- | --- | --- |
| X | Sue Chan | X | Sally Buonomo |
| X | Mike King |  | Bob Creveling |
|  | Biff Butler |  | Gene Anderson |
| X | Salim Mastan |  | Laura Eagan |
| X | Adele Jaimes | X | Bill Eagan |
|  | Steve Cho |  | Taskeen Fatehdin |

Minutes

Sue: Met with Catellus regarding Fundraising Reception to be held on Sept. 9, 2005 @ Premier Pizza Sally and Adele to assist with registration at dinner To have somewhere between 100 to 135 donors

All: Reviewed mailing list and entered more add-ons See AI #30 and #31

Jack: A strategic group will be formed to call quick meetings to make decisions. Group will include: Jack, Steve, Bill, Laura, Sally, Mike and Sue.

Action Items

| ID | Open Date | Description | Assigned to | Target Date | Date Closed |
| --- | --- | --- | --- | --- | --- |
| 13 | 6-6-05 | Find out if the Boy Scouts are interested in doing a sporting event with us. | To be assigned | TBD |  |
| 14 | 6-6 | Ask Steve Cho to look into information on cash box donations. (still to look into) | Mike King | 7-25-05 | 7-25-05 |
| 15 | 6-6 | look into donations by community groups (names of clubs needed) See AI # 19 | Gene Anderson & Les | 7-25-05 8-8-05 |  |
| 16 | 6-6 | Contact PGE, Alameda County Water and BFI and Comcast so enclose information about CF in their mailings or on their TV channel. Discussion was held (7-25-05) to have companies send information as inserts in with their billing. | Bill | 7-25-05 8-08-05 |  |
| 17 | 6-6 | Look into school bake and notify Salim about looking into “50/50 and solicit money from school children.” Salim to contact Moina On Education Team | Taskeen & Salim | 7-25-05 8-8-05 |  |
| 19 | 6-23 | Present to various clubs regarding commitment to raise money$ for CF (with AI # 15) Joint-Subcommittee to | Gene Anderson & Les TBA | TBD |  |
| 22 | 6-30 | Donation information to be put on CF website | Sue | 7-25-05 | 7-25-05 |
| 23 | 6-30 | Enter information on website regarding the security of making donation | Mike | 7-25-05 | 7-25-05 |
| 24 | 6-30 | Develop budget for FR Committee and send to Thomas | Jack | 7-25-05 | 7-25-05 |
| 25 | 6-30 | Follow up on Pledges, and Businesses not yet pledged but attended dinner | Laura | 7-25-05 | 7-25-05 |
| 26 | 6-30 | Approach Rotary Clubs and “pitch” CF to new incoming presidents | Bill and Mayor Bob | 7-25-05 8-22-05 |  |
| 27 | 7-11 | Jack will look into how much programs would cost should we decide to hand them out at the Sept. celebration. | Jack | 7-25-05 8-8-05 |  |
| 28 | 7-11 | Finalize the 2nd tier dinner invite list | Mike | 7-25-05 | 7-25-05 |
| 29 | 7-25 | Develop and Action Plan, Budget and a To Do List with milestones regarding calls to other businesses and households (70,000) | Salim | 8-08-05 |  |
| 30 | 7-25 | Set up Excel Spread Sheet with donors given by Salim. Email to Salim and cc Jack | Adele | 7-25-05 |  |
| 31 | 7-25 | Compete Excel sent by Adele with names of Contacts, Addresses and Phone #’s | Salim | 7-29-05 |  |

Steve:

Do follow up calls for donations to:

- Bank of America (Elaine Johnson)

- CA Savings Bank (Rosa Cantz)

- Indo American Federation (Jeevan Zutshi)

- Federation of Indo Americans (Dr. Ramesh Japra)

- Indo Americans for Better Community (Rakesh Sharma)

- Fed. of Indo. Americans AND Indo. Amer. Fed.

- US Bank (Barbara Varnell)

Sue:

Do follow up calls for donations to:

- Comcast (Hank Fore & Rachelle Guillen)

- DeSilva Group (Joe Cusenza )

- Home Advantage Corp. (Salim Mastan & Rarana Nadim Ahmed)

- Kaiser Perm. (Colleen McKeown)

Laura & Bill:

Do follow up calls for donations to:

- Bay Cities (Eric Barker)

- Granite Construction (Dave Donnelly)

- Dutra Ent. (John & Bernadine Dutra)

- Sunhill/Capital Ave. Partners (Jerry Hunt)

- Thermawave (Boris Lipkin)

- Top Grade (Bill Gates)

- Topline (President Philip Su and Mr. Tony Morici)

- Unitek (Paul & Shiva Afshar)

- Western Digital (Terry Bergh)

Dom:

Do follow up calls for donations to:

- SBC (Shiyama & Neale Clunie)

Unassigned to fundraising committee due to expected donation:

- Ohlone (Rick Geha) – Irene planned to call.

Next Meeting

| Date: | August 22, 2005 |
| --- | --- |
| Time: | 6:45 p.m. – 8:30 p.m. |
| Location: | CF Office on Eggers |
| Facilitator: | Jack Rogers |
| Scribe: | Adele Jaimes |